## Sheet1
Months before Fair | Days Before Fair | Target Date | Lead | Task Category | Activity Description | Status/Notes
|  |  |  | Note | Bold indicates activity completed
|  | 2013-03-15 | Judy Day | Overall Coordination | NC Science and Engineering Fair | Meredith College
Regional Fair
|  | 2014-01-24 |  |  | YOUR FAIR
9 | 270 | 2013-04-29 |  | Outreach to FF | set up communication with all feeder fairs
8 | 240 | 2013-05-29 |  | Outreach to FF | contact public schools, charters, private schools, homeschool associations,
9 | 270 | 2013-04-29 |  | Overall coordination | Form a committee and establish policies | e.g. how many projects can come from each feeder fair,
9 | 270 | 2013-04-29 |  | Overall coordination | Recruit a Science Fair Team
9 | 270 | 2013-04-29 |  | Venue | calculate space needs
9 | 270 | 2013-04-29 |  | Venue | decide on dates
9 | 270 | 2013-04-29 |  | Venue | determine schedule
9 | 270 | 2013-04-29 |  | Venue | get administrative approval
9 | 270 | 2013-04-29 |  | Venue | reserve venue
9 | 270 | 2013-04-29 |  | Venue | arrange extra security
9 | 270 | 2013-04-29 |  | Venue | arrange extra custodial support
9 | 270 | 2013-04-29 |  | Venue | arrange for tables
3 | 90 | 2013-10-26 |  | Venue | plan for parking
3 | 90 | 2013-10-26 |  | Venue | plan for refreshments
3 | 90 | 2013-10-26 |  | Venue | plan for supervision of students on site
3 | 90 | 2013-10-26 |  | Venue | keep in touch with venue manager as fair approaches
3 | 90 | 2013-10-26 |  | Venue | consider additional educational and entertainment
1 | 30 | 2013-12-25 |  | Venue | make directional signs for students, families, judges
1 | 30 | 2013-12-25 |  | Venue | check on tables and set up plans
1 | 30 | 2013-12-25 |  | Venue | check on arrangements for refreshments
9 | 270 | 2013-04-29 |  | Website | set up fair website: dates, deadlines, rules, policies, resources
6 | 180 | 2013-07-28 |  | Website | be sure website is up to date with current information
2 | 60 | 2013-11-25 |  | Outreach to FF | send out reminders of registration procedure, rules, schedule, parking, set up info etc
9 | 270 | 2013-04-29 |  | SRC/IRB | recruit SRC/IRB members
9 | 270 | 2013-04-29 |  | SRC/IRB | establish chair, set meeting schedule
7 | 210 | 2013-06-28 |  | SRC/IRB | train members, review rules
6 | 180 | 2013-07-28 |  | SRC/IRB | set up procedures to review projects before experimentation | special attention to possibility of students working in summer
1 | 30 | 2013-12-25 |  | SRC/IRB | review all project paperwork prior to fair
4 | 120 | 2013-09-26 |  | Registration | establish procedure, figure out fees, determine deadlines | consider using Science Fair in a Box
1 | 30 | 2013-12-25 |  | Registration | accept registrations, deposit checks, get paperwork to SRC
0.5 | 15 | 2014-01-09 |  | Registration | create program listing projects plus schedule for day
0.5 | 15 | 2014-01-09 |  | Registration | create nametags and project labels
0.5 | 15 | 2014-01-09 |  | Registration | assign projects to spots
0 | 0 | 2014-01-24 |  | Registration | greet students, pass out packets, direct students to spots for set up
1.5 | 45 | 2013-12-10 |  | Set Up/Display and Safety | plan organization to receive projects
1.5 | 45 | 2013-12-10 |  | Set Up/Display and Safety | recruit a team to do the display and safety check
1.5 | 45 | 2013-12-10 |  | Set Up/Display and Safety | create a display and safety checklist form
0.05 | 1.5 | 2014-01-22 12:00 |  | Set Up/Display and Safety | Set up the venue
0.5 | 15 | 2014-01-09 |  | Set Up/Display and Safety | train members, review rules
0 | 0 | 2014-01-24 |  | Set Up/Display and Safety | direct students and parents to set up projects
0 | 0 | 2014-01-24 |  | Set Up/Display and Safety | check each project display
0 | 0 | 2014-01-24 |  | Set Up/Display and Safety | be sure students are supervised at all times
0 | 0 | 2014-01-24 |  | Set Up/Display and Safety | clean up tasks
6 | 180 | 2013-07-28 |  | Judges | Recruit, register judges
2 | 60 | 2013-11-25 |  | Judges | assign judges to categories
2 | 60 | 2013-11-25 |  | Judges | send all judges regular reminders
2 | 60 | 2013-11-25 |  | Judges | hold a training event for judges, send out training information
6 | 180 | 2013-07-28 |  | Overall coordination | Plan schedule for the day
0 | 0 | 2014-01-24 |  | Judges | greet judges
0 | 0 | 2014-01-24 |  | Judges | orient judges
| 0 | 2014-01-24 |  | Judges
Formulas:
Target Date = C5-[Days Before Fair]